SIMATS ENGINEERING (SAVEETHA SCHOOL OF ENGINEERING)

Department of Computer Science and Engineering

CO1 ASSESSMENT TOOL 2 – Agile Sprint Planning & User Story Workshop

| Course Code: CSA10 / CSA1023 | Course Title: Software Engineering |
| --- | --- |
| CO Assessed: CO1 | Assessment: Assessment Tool 2 – Agile Sprint Planning & User Story Workshop |
| Weightage: 20% | Total Marks: 25 |
| CO1 Statement: Apply advanced methodologies and agile project management techniques to manage software projects effectively |  |
| Student Name: Shaik Afra Aiman | Reg. No.: 1911260412 |
| Date: 9th Oct 2026 | Duration: 60 minutes |

Code of Conduct

I Shaik Afra Aiman (Name / Reg No) certify that this submission is my original work and that I have adhered to the guidelines specified for this assessment. I understand that any violation of academic integrity rules will result in disciplinary action.

Signature of the Student : Afra

AGILE SPRINT PLANNING & USER STORY WORKSHOP

Problem Statement 34: Intelligent Public Service Complaint Resolution Platform

Project Name: Civic Resolve

# Introduction

Public organizations such as municipal corporations, water boards, electricity utilities and transport authorities receive a very large number of complaints every day about roads, water supply, sanitation, public transport, utilities and other civic services. In most of these organizations, the complaints are still received through registers, phone calls, e-mails and walk-ins, and they are classified and forwarded to the concerned department by hand. This manual handling delays resolution causes complaints to reach the wrong department, and makes it very difficult to measure whether service-level targets are being met.

The problem statement assigned to me is to design and develop an Intelligent Public Service Complaint Resolution Platform that classifies complaints, prioritizes them, routes them to the appropriate departments, tracks their progress and provides citizens with status updates. The platform must support scalable APIs, role-based access, workflow automation, monitoring, analytics, testing and CI/CD, and the automated classification must remain reviewable and transparent.

Table 1: Project at a glance

| Item | Details |
| --- | --- |
| Project name | Civic Resolve – Intelligent Public Service Complaint Resolution Platform |
| Agile framework | Scrum (time-boxed sprints, product backlog, sprint backlog, increments) |
| Sprint length | 2 weeks (10 working days) |
| Estimation technique | Planning Poker using the Fibonacci sequence (1, 2, 3, 5, 8, 13) |
| Proposed technology stack | React front end, Node.js / Express REST APIs, PostgreSQL database, Python (scikit-learn) classification service, Docker, GitHub Actions for CI/CD, Prometheus and Grafana for monitoring |
| Planned release | Six sprints (12 weeks); this document plans Sprint 1 in detail |

Objectives: collect and classify public complaints; prioritize issues according to urgency and impact; route complaints to responsible departments; track resolution status and service-level targets; provide citizen notifications and dashboards; implement secure APIs, testing, CI/CD and monitoring; and maintain transparency and audit trails.

Expected outcomes: reduced complaint-processing delays, improved departmental coordination, increased transparency of service delivery, measurable resolution performance, reduced manual administrative work and improved citizen access to service information.

# 1. Project Vision and Stakeholders

## 1.1 Product vision

Vision statement: “To build a transparent, fast and trustworthy digital platform on which every citizen can register a civic complaint in minutes, have it automatically understood, prioritized and sent to the right department, and follow its progress until it is resolved, while giving the administration reliable data to improve public services.”

Table 2: Product vision board

| Element | Description |
| --- | --- |
| For | Citizens, municipal departments and city administrators |
| Who need | A quick, transparent and accountable way to report civic problems and get them resolved within defined service levels |
| The product is | Civic Resolve, a web-based complaint resolution platform |
| That | Collects complaints, classifies them with a reviewable rule and machine-learning model, prioritizes them by urgency and impact, routes them to the responsible department, tracks service-level targets and keeps citizens informed at every stage |
| Unlike | Manual registers, phone-based complaint handling and spreadsheet tracking, which are slow, error-prone and not auditable |
| Our product | Reduces processing delay, shows how every automated decision was made, records a complete audit trail and gives measurable performance data |

## 1.2 Project objectives and success measures

The objectives given in the problem statement have been converted into measurable targets so that the success of every sprint can be verified.

Table 3: SMART objectives

| ID | Objective | Success measure | Target |
| --- | --- | --- | --- |
| O1 | Collect and classify complaints | Classification accuracy on a labelled test set | At least 85% by Sprint 3 |
| O2 | Prioritize by urgency and impact | Critical complaints flagged and shown at the top of the queue | Within 1 minute, 100% |
| O3 | Route to responsible department | Complaints routed without manual intervention | At least 90% |
| O4 | Track resolution and service-level targets | Complaints resolved within SLA | At least 85% |
| O5 | Citizen notifications and dashboards | Notification delivered after a status change | Within 2 minutes, 95% |
| O6 | Secure APIs, testing, CI/CD, monitoring | Test coverage, pipeline time, API response time (95th percentile) | 70% coverage, under 10 min, under 500 ms |
| O7 | Transparency and audit trail | Important actions recorded in the audit log | 100% |

## 1.3 Project scope

In scope: citizen web portal; officer, supervisor, administrator and auditor consoles; automated classification and prioritization with manual review; routing and workflow automation; SLA tracking and escalation; e-mail and SMS notifications; dashboards, analytics and reports; audit trail, secure REST APIs, CI/CD and monitoring.

Out of scope (current release): native mobile apps, online payments, integration with legacy ERP and billing systems, voice (IVR) and chatbot channels, image-based classification and GIS route optimization.

## 1.4 Stakeholder identification

Stakeholders were identified by asking who uses the system, who is affected by its decisions, who pays for it, who builds it and who audits it. The stakeholder register is given below.

Table 4: Stakeholder register

| Stakeholder | Role in the project | Interest and expectation | Influence |
| --- | --- | --- | --- |
| Citizens | Primary end users who submit and track complaints | Easy submission, quick action, regular status updates, privacy of personal data | Medium |
| Complaint intake officers | Register complaints received through phone or help desk | Simple data entry screen, duplicate detection | Low |
| Department officers (Roads, Water, Sanitation, Transport, Utilities) | Receive and resolve routed complaints | Correct routing, clear priority, manageable workload | Medium |
| Field technicians | Carry out the repair or service work on site | Clear task details, location, ability to update completion on mobile browser | Low |
| Department supervisors / heads | Monitor performance and handle escalations | SLA dashboards, reassignment and escalation control | High |
| City administrator / Commissioner | Executive sponsor and decision maker | Transparency, measurable performance, trend analysis for planning | High |
| Product Owner | Owns the product backlog and decides priorities | Maximum business value in every sprint | High |
| Scrum Master | Facilitates Scrum events and removes impediments | Smooth team flow, adherence to Scrum | Medium |
| Development, QA and DevOps team | Designs, builds, tests, deploys and monitors the product | Clear stories, realistic sprint scope, good tools | High |
| System administrator | Manages users, roles and configuration | Easy role management, secure configuration | Medium |
| Auditors / oversight bodies | Verify accountability and compliance | Tamper-proof audit trail, explainable automated decisions | High |

## 1.5 Scrum team and roles

Table 5: Scrum team structure

| Role | Responsibility | Members |
| --- | --- | --- |
| Product Owner | Maintains the product backlog, defines priorities and accepts completed stories | 1 |
| Scrum Master | Coaches the team on Scrum, conducts events, removes impediments | 1 |
| Backend developers (BD1, BD2) | APIs, database, classification service, routing engine | 2 |
| Frontend developer (FD) | Citizen portal and officer screens | 1 |
| DevOps engineer (DO) | CI/CD pipeline, deployment, monitoring | 1 |
| QA engineer (QA) | Test planning, automation and acceptance testing | 1 |

## 1.6 Assumptions and constraints

Assumptions: the administration will provide the list of departments, wards and complaint categories before Sprint 1; at least 500 past (or synthetic) complaints are available to train the classifier; the Product Owner is available during the sprint; and SMS and e-mail sandbox accounts are available from Sprint 2.

Constraints: the release must be completed in six sprints (12 weeks); personal data of citizens must be protected as per the data protection policy; the first release is web-based only and must work on mobile browsers; and every automated decision must be reviewable by a human officer.

# 2. Epics and User Stories

## 2.1 Epics

The requirements in the problem statement were grouped into nine epics. An epic is a large body of work that is too big for one sprint and is therefore split into several user stories.

Table 6: Epic list

| Epic | Epic name | Description | Objective |
| --- | --- | --- | --- |
| E1 | Complaint submission and intake | Citizens and officers register complaints with details and attachments and receive a reference ID | O1 |
| E2 | Authentication and role-based access | Secure registration, login, roles and permissions for every type of user | O6, O7 |
| E3 | Classification and prioritization | Automatic category and priority assignment, human review and explanation of decisions | O1, O2, O7 |
| E4 | Routing and workflow automation | Routing to departments, reassignment, field assignment and escalation | O3 |
| E5 | Resolution tracking and SLA management | Status lifecycle, SLA targets, resolution proof and citizen confirmation | O4 |
| E6 | Citizen notifications and dashboards | Notifications, complaint tracking page and public dashboard | O5 |
| E7 | Analytics and reporting | Supervisor dashboard, trend analysis and report export | O4 |
| E8 | Transparency, audit and security | Audit trail, audit search and secure APIs | O6, O7 |
| E9 | Platform engineering | CI/CD, automated testing, monitoring and API documentation | O6 |

## 2.2 User story format and quality check

All user stories are written in the format As a <user>, I want <feature>, so that <benefit>. Each story was checked against the INVEST criteria: Independent, Negotiable, Valuable, Estimable, Small and Testable. Stories that were found too large (for example, “manage complaints”) were split until they could be completed within one sprint.

## 2.3 Product backlog – user stories

Table 7: User stories grouped by epic

| ID | User story |
| --- | --- |
| Epic E1 – Complaint submission and intake |  |
| US-01 | As a citizen, I want to submit a complaint by entering a title, description and location (ward and address), so that the concerned authority becomes aware of the civic problem without visiting an office. |
| US-02 | As a citizen, I want to attach up to three photographs (maximum 5 MB each) to my complaint, so that the department can understand and verify the problem quickly. |
| US-03 | As a citizen, I want to receive a unique complaint reference ID immediately after submission, so that I can track and refer to my complaint in future. |
| US-04 | As an intake officer, I want to register a complaint on behalf of a citizen who calls or visits the help desk, so that citizens without internet access are also served. |
| US-05 | As an intake officer, I want the system to warn me when a similar complaint already exists for the same location and category, so that duplicate work is avoided and related complaints are linked. |
| Epic E2 – Authentication and role-based access |  |
| US-06 | As a citizen, I want to register and log in securely using my e-mail or mobile number with OTP verification, so that my complaints and personal data are protected. |
| US-07 | As a system administrator, I want to create staff accounts and assign roles to them, so that every employee gets only the access required for his or her duties. |
| US-08 | As a system administrator, I want the platform to enforce role-based access on every screen and API, so that unauthorized users cannot view or change complaint data. |
| Epic E3 – Classification and prioritization |  |
| US-09 | As a complaint reviewer, I want every new complaint to be classified automatically into a service category with a confidence score, so that manual sorting effort is reduced. |
| US-10 | As a department supervisor, I want complaints to be given a priority (Critical, High, Medium or Low) based on urgency and public impact, so that urgent problems such as a burst water pipe or an open manhole are attended first. |
| US-11 | As a complaint reviewer, I want to override the automatic category or priority and record a reason, so that wrong classifications are corrected and the system remains under human control. |
| US-12 | As a complaint reviewer, I want to see why the system chose a particular category and priority (keywords, rules, score), so that automated decisions remain transparent and reviewable. |
| Epic E4 – Routing and workflow automation |  |
| US-13 | As a department officer, I want complaints to be routed automatically to my department based on category and ward, so that I receive only the complaints I am responsible for. |
| US-14 | As a department supervisor, I want to reassign a wrongly routed complaint to another department with a reason, so that the complaint reaches the right authority without delay. |
| US-15 | As a department officer, I want to assign a complaint to a field technician, so that the work is carried out on site and its ownership is clear. |
| US-16 | As a department head, I want complaints that are close to breaching their SLA to be escalated automatically to the next level, so that delays are prevented. |
| Epic E5 – Resolution tracking and SLA management |  |
| US-17 | As a department officer, I want to update the status of a complaint (Registered, Assigned, In Progress, Resolved, Closed, Reopened), so that progress is always current. |
| US-18 | As a department head, I want to configure service-level targets (resolution time) for each category and priority, so that performance can be measured against defined standards. |
| US-19 | As a field technician, I want to add resolution notes and a completion photograph, so that the work done is documented as evidence. |
| US-20 | As a citizen, I want to confirm the resolution or reopen the complaint if the problem still exists, so that complaints are closed only when I am satisfied. |
| Epic E6 – Citizen notifications and dashboards |  |
| US-21 | As a citizen, I want to receive e-mail or SMS notifications whenever the status of my complaint changes, so that I do not have to keep checking the portal. |
| US-22 | As a citizen, I want to view my complaint on a dashboard with a status timeline, so that I know who is working on it and when it is expected to be resolved. |
| US-23 | As a member of the public, I want to see a public dashboard with ward-wise complaint and resolution statistics, so that I can judge how well the civic body is performing. |
| Epic E7 – Analytics and reporting |  |
| US-24 | As a department supervisor, I want a dashboard showing open complaints, aging complaints and SLA compliance, so that I can manage my team’s workload. |
| US-25 | As a city administrator, I want trend and hot-spot analysis of complaints by category and ward, so that resources and preventive actions can be planned. |
| US-26 | As a city administrator, I want to export performance reports in PDF and CSV formats, so that I can share them in review meetings. |
| Epic E8 – Transparency, audit and security |  |
| US-27 | As an auditor, I want every important action in the system to be recorded in a tamper-proof audit trail, so that accountability can be established. |
| US-28 | As an auditor, I want to search and filter audit logs by user, date, complaint and action, so that I can investigate any dispute quickly. |
| US-29 | As a security officer, I want all APIs to be protected using token-based authentication, input validation and rate limiting, so that the platform is safe from misuse and attacks. |
| Epic E9 – Platform engineering |  |
| US-30 | As a developer, I want an automated CI/CD pipeline that builds, tests and deploys the application, so that changes are delivered quickly and reliably. |
| US-31 | As a DevOps engineer, I want health monitoring and alerts for the application, database and APIs, so that failures are detected and fixed before citizens are affected. |
| US-32 | As a QA engineer, I want an automated regression test suite with at least 70% code coverage, so that new releases do not break existing features. |
| US-33 | As an external system integrator, I want well-documented, versioned REST APIs (OpenAPI), so that other government systems can integrate with the platform easily. |

# 3. Acceptance Criteria

Acceptance criteria describe the conditions that must be satisfied before the Product Owner accepts a story as done. They have been written in the Given–When–Then format and each criterion is specific, measurable and testable. Detailed criteria are given below for the eight user stories selected for Sprint 1, followed by short criteria for the stories planned for Sprint 2.

Table 8: Acceptance criteria for the Sprint 1 user stories

| No. | Given | When | Then |
| --- | --- | --- | --- |
| 3.1 US-30: Automated CI/CD pipeline |  |  |  |
| AC-30.1 | A developer opens a pull request on a feature branch | The pipeline is triggered | Build, lint and unit tests run automatically and the result is shown on the pull request within 10 minutes |
| AC-30.2 | The pipeline has failed on a pull request | The developer tries to merge the pull request | The merge is blocked until the pipeline passes and at least one reviewer approves |
| AC-30.3 | A pull request is merged into the main branch and the pipeline passes | The deployment stage runs | A Docker image is built and deployed to the staging server and the team channel receives a success or failure message |
| 3.2 US-06: Citizen registration and login |  |  |  |
| AC-06.1 | A new citizen is on the registration page | He or she enters a valid name, e-mail or mobile number and a password of at least 8 characters with one digit and one special character, and verifies the OTP | The account is created and a success message is displayed within 3 seconds |
| AC-06.2 | An account already exists with the same e-mail or mobile number | A user tries to register again | The system refuses the registration, shows “Account already exists” and creates no duplicate record |
| AC-06.3 | A registered and verified citizen is on the login page | Valid credentials are entered | A token valid for 30 minutes is issued and the citizen is taken to his or her dashboard |
| AC-06.4 | Five consecutive wrong passwords have been entered | A sixth attempt is made | The account is locked for 15 minutes and the event is written to the audit log |
| 3.3 US-08: Role-based access control |  |  |  |
| AC-08.1 | A user is logged in with the Citizen role | The user calls an officer-only screen or API | The system returns HTTP 403 and no complaint data is shown |
| AC-08.2 | A Roads department officer is logged in | The officer opens the complaint list | Only complaints routed to the Roads department are displayed |
| AC-08.3 | A request is sent without a valid token | Any protected API is called | The system returns HTTP 401 and no data |
| AC-08.4 | The administrator opens role management | The roles page loads | The six roles (Citizen, Intake Officer, Department Officer, Supervisor, Administrator, Auditor) and their permissions are listed |
| 3.4 US-01: Submit a complaint |  |  |  |
| AC-01.1 | A logged-in citizen is on the complaint form | He or she enters a title (5 to 100 characters), a description (20 to 1000 characters), ward and address, and clicks Submit | The complaint is saved with the status “Registered” and a confirmation is displayed within 3 seconds |
| AC-01.2 | A mandatory field is empty or invalid | The citizen clicks Submit | Field-level error messages are shown and nothing is saved |
| AC-01.3 | The description is longer than 1000 characters | The citizen continues typing | A character counter is shown and additional input is blocked |
| AC-01.4 | 100 users submit complaints at the same time | The load test is executed on staging | No request fails and 95% of the requests complete within 2 seconds |
| 3.5 US-03: Unique complaint reference ID |  |  |  |
| AC-03.1 | A complaint has been saved successfully | The confirmation page is displayed | A unique ID in the format CMP-YYYY-NNNNNN (for example CMP-2026-000125) is shown with a copy option |
| AC-03.2 | Two complaints are submitted at the same moment | Both are saved | The two complaints receive different IDs and the database rejects any duplicate ID |
| AC-03.3 | A citizen opens “My Complaints” | The list loads | The complaint appears with its ID, submission date and current status |
| 3.6 US-09: Automatic complaint classification |  |  |  |
| AC-09.1 | A new complaint is registered | The classification service is called | One of six categories (Roads, Water Supply, Sanitation, Transport, Electricity and Utilities, Other Civic Services) is assigned with a confidence score between 0 and 1 within 5 seconds |
| AC-09.2 | The confidence score is 0.60 or above | The result is saved | The category is applied automatically and the status becomes “Classified” |
| AC-09.3 | The confidence score is below 0.60 | The result is saved | The complaint is marked “Manual Review Required” and appears in the reviewer queue |
| AC-09.4 | An officer opens a classified complaint | The details page loads | The top three keywords or rules that influenced the decision are displayed |
| AC-09.5 | A labelled set of 100 unseen complaints is available | The model is evaluated | Accuracy is at least 80% in Sprint 1 (target of 85% by Sprint 3) |
| 3.7 US-13: Automatic routing to departments |  |  |  |
| AC-13.1 | A complaint has a category and a ward | The routing engine runs | The complaint is assigned to the department mapped to that category and appears in its queue within 10 seconds |
| AC-13.2 | The category is “Other Civic Services” or the complaint needs manual review | The routing engine runs | The complaint is placed in the General Grievance Cell queue |
| AC-13.3 | A complaint has been routed | An officer opens it | The department, rule applied and routing time are visible |
| AC-13.4 | No active officer exists for the ward in that department | The routing engine runs | The complaint goes to the department supervisor’s queue |
| 3.8 US-27: Audit trail |  |  |  |
| AC-27.1 | Any of these events occurs: login, complaint creation, classification, routing or role change | The action is completed | An audit record with user ID, action, entity ID, UTC timestamp and old and new values is stored |
| AC-27.2 | An audit record exists | Any user or API tries to edit or delete it | The operation is rejected because the audit table is append-only |
| AC-27.3 | A complaint has more than 100 audit records | The history is requested by complaint ID | The records are returned in chronological order within 3 seconds |

# 4. Product Backlog Prioritization

## 4.1 Prioritization approach

The backlog was prioritized together with the (assumed) Product Owner using three factors: business value (scored from 1 to 10), customer need and dependencies between stories. The MoSCoW technique (Must have, Should have, Could have, Won’t have now) was then used to confirm the ranking.

## 4.2 Prioritized product backlog

Table 9: Prioritized product backlog

| Rank | ID | User story (short title) | Business value | Depends on | MoSCoW | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | US-30 | Automated CI/CD pipeline | 8 | None | Must | 1 |
| 2 | US-06 | Citizen registration and login | 9 | None | Must | 1 |
| 3 | US-08 | Role-based access control | 9 | US-06 | Must | 1 |
| 4 | US-01 | Submit a complaint | 10 | US-06 | Must | 1 |
| 5 | US-03 | Unique complaint reference ID | 8 | US-01 | Must | 1 |
| 6 | US-09 | Automatic classification | 10 | US-01 | Must | 1 |
| 7 | US-13 | Automatic routing to department | 10 | US-09 | Must | 1 |
| 8 | US-27 | Audit trail | 8 | US-06 | Must | 1 |
| 9 | US-10 | Priority by urgency and impact | 10 | US-09 | Must | 2 |
| 10 | US-11 | Override category / priority | 9 | US-09, US-10 | Must | 2 |
| 11 | US-17 | Update complaint status | 9 | US-13 | Must | 2 |
| 12 | US-15 | Assign to field technician | 8 | US-13 | Must | 2 |
| 13 | US-07 | Create staff accounts and roles | 7 | US-08 | Must | 2 |
| 14 | US-22 | Citizen tracking dashboard | 8 | US-03, US-17 | Must | 3 |
| 15 | US-21 | Status notifications | 9 | US-17 | Must | 3 |
| 16 | US-12 | Explanation of automated decisions | 8 | US-09, US-10 | Must | 3 |
| 17 | US-18 | SLA configuration | 8 | US-10 | Must | 3 |
| 18 | US-19 | Resolution notes and photo | 7 | US-15, US-17 | Should | 3 |
| 19 | US-29 | Secure API protection | 9 | US-08 | Must | 3 |
| 20 | US-16 | SLA-based escalation | 8 | US-18 | Should | 4 |
| 21 | US-14 | Reassign complaint | 7 | US-13 | Should | 4 |
| 22 | US-20 | Citizen confirms or reopens | 7 | US-17, US-21 | Should | 4 |
| 23 | US-32 | Automated regression suite | 8 | US-30 | Must | 4 |
| 24 | US-02 | Attach photographs | 6 | US-01 | Should | 4 |
| 25 | US-04 | Intake officer registers complaint | 6 | US-01, US-08 | Should | 4 |
| 26 | US-24 | Supervisor dashboard | 8 | US-17, US-18 | Should | 5 |
| 27 | US-31 | Monitoring and alerts | 7 | US-30 | Should | 5 |
| 28 | US-28 | Audit log search | 6 | US-27 | Should | 5 |
| 29 | US-33 | API documentation (OpenAPI) | 5 | US-29 | Should | 5 |
| 30 | US-25 | Trend and hot-spot analysis | 7 | US-24 | Could | 6 |
| 31 | US-26 | Export reports | 5 | US-24 | Could | 6 |
| 32 | US-23 | Public dashboard | 6 | US-24 | Could | 6 |
| 33 | US-05 | Duplicate complaint warning | 5 | US-01, US-09 | Could | 6 |

## 4.3 Release plan

Table 10: Sprint-wise release plan

| Sprint | Theme | Main stories |
| --- | --- | --- |
| Sprint 1 | Foundation, complaint intake and intelligent routing | US-30, US-06, US-08, US-01, US-03, US-09, US-13, US-27 |
| Sprint 2 | Prioritization, review and workflow | US-10, US-11, US-17, US-15, US-07 |
| Sprint 3 | Citizen experience, SLA and security | US-22, US-21, US-12, US-18, US-19, US-29 |
| Sprint 4 | Escalation, reopening, testing and attachments | US-16, US-14, US-20, US-32, US-02, US-04 |
| Sprint 5 | Monitoring, dashboards and audit search | US-24, US-31, US-28, US-33 |
| Sprint 6 | Analytics, reports and hardening | US-25, US-26, US-23, US-05, performance testing, final release |

## 4.4 Justification of the order

Login, access control and complaint submission come first because every other feature depends on them. Classification and routing (US-09, US-13) deliver the main value of the project and carry the highest technical risk, so they start in Sprint 1. The CI/CD pipeline (US-30) is ranked first because all later stories are built and tested through it, and the audit trail (US-27) is added early because it is cheaper to log events from the beginning. Dashboards and analytics depend on data from earlier sprints and are planned later.

# 5. Sprint Backlog Planning (Sprint 1)

## 5.1 Sprint details

Table 11: Sprint 1 details

| Item | Details |
| --- | --- |
| Sprint duration | 2 weeks (10 working days) |
| Team size | 5 developers and testers (BD1, BD2, FD, DO, QA) plus the Product Owner and Scrum Master |
| Available capacity | 5 members × 10 days × 6 productive hours = 300 hours (the remaining 2 hours per day are used for Scrum events and communication) |
| Planned effort | 259 hours (about 86% of capacity) – the remaining 41 hours are kept as buffer for defects, rework and unplanned work |
| Committed story points | 34 story points (8 user stories) |
| Sprint theme | Foundation, complaint intake and intelligent routing |

## 5.2 Selection of stories for Sprint 1

The eight highest-ranked stories of the product backlog were selected. Together they give the team a thin but complete slice of the product: a citizen can register, log in, submit a complaint, receive a reference ID and the complaint is automatically classified and routed to the right department, while the pipeline, access control and audit trail provide the technical base for later sprints. Priority calculation (US-10) was deliberately left for Sprint 2 because it depends on the classification output, and all complaints are given the default priority “Medium” in Sprint 1.

Table 12: Selected user stories for Sprint 1

| ID | User story | Epic | Story points | Priority |
| --- | --- | --- | --- | --- |
| US-30 | Automated CI/CD pipeline | E9 | 3 | Must |
| US-06 | Citizen registration and login | E2 | 3 | Must |
| US-08 | Role-based access control | E2 | 5 | Must |
| US-01 | Submit a complaint | E1 | 5 | Must |
| US-03 | Unique complaint reference ID | E1 | 2 | Must |
| US-09 | Automatic complaint classification | E3 | 8 | Must |
| US-13 | Automatic routing to department | E4 | 5 | Must |
| US-27 | Audit trail | E8 | 3 | Must |
|  | Total |  | 34 |  |

## 5.3 Task breakdown

Each selected story has been divided into development tasks of at most 14 hours so that progress can be seen every day in the daily Scrum. The owner column shows the role expected to take the task; the team is cross-functional and may swap tasks.

Table 13: Sprint 1 task breakdown

| Task | Description | Owner | Hours |
| --- | --- | --- | --- |
| US-30 – Automated CI/CD pipeline (3 SP) – total 24 hours |  |  |  |
| T1 | Create Git repository, branching strategy and pull-request review rules | DO | 4 |
| T2 | Configure CI pipeline: build, lint and unit-test stages | DO | 8 |
| T3 | Create Docker images and automatic deployment to the staging server | DO | 8 |
| T4 | Add status checks, merge blocking and team-channel notifications | DO | 4 |
| US-06 – Citizen registration and login (3 SP) – total 30 hours |  |  |  |
| T5 | Design user table schema and database migration | BD1 | 3 |
| T6 | Develop registration API with e-mail / mobile OTP verification | BD1 | 8 |
| T7 | Develop login API with password hashing, JWT token and lock-out rule | BD1 | 6 |
| T8 | Build registration and login screens | FD | 8 |
| T9 | Write unit and integration tests for registration and login | QA | 5 |
| US-08 – Role-based access control (5 SP) – total 29 hours |  |  |  |
| T10 | Define roles and permission matrix with the Product Owner | BD1 | 3 |
| T11 | Create role and permission models in the database | BD1 | 6 |
| T12 | Implement authorization middleware for all protected APIs | BD1 | 8 |
| T13 | Implement role-based menus and page guards in the front end | FD | 6 |
| T14 | Write security test cases for unauthorized access (401 / 403) | QA | 6 |
| US-01 – Submit a complaint (5 SP) – total 36 hours |  |  |  |
| T15 | Design complaint table and category / ward master data | BD2 | 4 |
| T16 | Develop complaint submission API with validation rules | BD2 | 10 |
| T17 | Build complaint submission form (title, description, location) | FD | 10 |
| T18 | Add ward and address selector with field-level error messages | FD | 6 |
| T19 | Write test cases for valid, invalid and boundary inputs | QA | 6 |
| US-03 – Unique complaint reference ID (2 SP) – total 9 hours |  |  |  |
| T20 | Implement ID generator in the format CMP-YYYY-NNNNNN with a unique constraint | BD2 | 3 |
| T21 | Build confirmation page and “My Complaints” list | FD | 4 |
| T22 | Test ID uniqueness under concurrent submissions | QA | 2 |
| US-09 – Automatic complaint classification (8 SP) – total 62 hours |  |  |  |
| T23 | Collect and label at least 500 sample complaints and fix the six categories | BD2 | 8 |
| T24 | Develop keyword rule-based classifier as baseline | BD2 | 10 |
| T25 | Train and evaluate text classification model (TF-IDF with Logistic Regression) | BD2 | 14 |
| T26 | Expose classification as a REST service returning category and confidence | BD2 | 10 |
| T27 | Store confidence score and top keywords with the complaint for explanation | BD1 | 6 |
| T28 | Implement manual-review fallback for confidence below 0.60 | BD1 | 6 |
| T29 | Test model accuracy and service response time | QA | 8 |
| US-13 – Automatic routing to department (5 SP) – total 37 hours |  |  |  |
| T30 | Create department, officer and category-to-department mapping tables | BD1 | 5 |
| T31 | Develop routing engine using category and ward rules | BD2 | 10 |
| T32 | Build department queue API and officer queue screen | FD | 12 |
| T33 | Add in-app alert for new complaint in department queue | FD | 4 |
| T34 | Test routing for all category and ward combinations in the sample data | QA | 6 |
| US-27 – Audit trail (3 SP) – total 18 hours |  |  |  |
| T35 | Design append-only audit log schema | BD1 | 3 |
| T36 | Implement audit logging middleware | BD1 | 8 |
| T37 | Log login, complaint creation, classification and routing events | BD1 | 4 |
| T38 | Test that audit records cannot be edited or deleted | QA | 3 |
| Sprint-level tasks – total 14 hours |  |  |  |
| T39 | Prepare Swagger / API documentation and deployment notes | BD1 | 6 |
| T40 | End-to-end regression testing and demo preparation | QA | 8 |
|  | Total planned effort (against 300 hours of capacity) |  | 259 |

## 5.4 Definition of Done

Definition of Done: a story is done when its code is peer-reviewed and merged through a pull request, all acceptance criteria are tested and passed by QA, unit tests are written and the pipeline is green, relevant non-functional requirements are checked, API documentation is updated, the feature is deployed to staging and shown to the Product Owner, and no critical or high-severity defect remains open.

# 6. Effort Estimation Using Story Points

## 6.1 Estimation technique

Story points are a relative measure of the size of a story that combines the amount of work, the complexity and the uncertainty. The team used Planning Poker with the modified Fibonacci sequence (1, 2, 3, 5, 8, 13). Each member privately selects a card; if the cards differ widely, the highest and the lowest estimators explain their reasoning and the team votes again until it agrees. The Fibonacci scale was chosen because the gaps between numbers grow as stories become bigger, which reflects the fact that large stories cannot be estimated precisely.

Reference story: US-03 (Unique complaint reference ID) was taken as the baseline of 2 points because it is small, well understood and touches one table, one API and one screen. All other stories were compared with it.

## 6.2 Planning Poker results and justification

Table 14: Planning Poker votes (first round), final estimate and justification

| Story | BD1 | BD2 | FD | DO | QA | Final | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- |
| US-30 | 3 | 3 | 2 | 3 | 3 | 3 | Ready-made Actions and Docker templates; effort is mainly configuration and staging access. Low uncertainty. |
| US-06 | 3 | 3 | 5 | 3 | 3 | 3 | Standard OTP, JWT and hashing pattern; two screens and one table. Low uncertainty. |
| US-08 | 5 | 5 | 8 | 5 | 5 | 5 | Cuts across all APIs and screens; needs permission matrix, middleware and guards, so extra testing. Medium uncertainty. |
| US-01 | 5 | 5 | 5 | 5 | 8 | 5 | Work in all three layers with many validation cases but no technical unknowns. |
| US-03 | 2 | 2 | 2 | 1 | 2 | 2 | Reference story: one generator function with a unique constraint. |
| US-09 | 8 | 13 | 8 | 5 | 8 | 8 | Data preparation, model training, separate service, confidence and explanation; accuracy cannot be guaranteed. High uncertainty; round 2 all voted 8. |
| US-13 | 5 | 8 | 5 | 5 | 5 | 5 | Simple rules, but depends on classification output and needs both API and queue screen. Medium uncertainty. |
| US-27 | 3 | 3 | 5 | 3 | 3 | 3 | One middleware and an append-only table; effort is in logging every required event. |
| Total |  |  |  |  |  | 34 |  |

## 6.3 Capacity check and velocity

As this is the first sprint, no historical velocity is available. The commitment of 34 story points was therefore checked against the capacity in hours. The task estimates add up to 259 hours against a capacity of 300 hours, which leaves a buffer of about 14%. A sprint commitment above 90% of capacity would be risky for a new team, because the classification story contains experiments whose time cannot be predicted exactly. After Sprint 1 the actual completed points will be recorded as the team’s velocity and used for forecasting Sprints 2 to 6.

# 7. Sprint Goal and Expected Deliverables

## 7.1 Sprint goal

Sprint 1 Goal: “By the end of Sprint 1, a registered citizen can log in securely, submit a complaint and receive a unique reference ID, and the platform automatically classifies the complaint, routes it to the responsible department queue and records every step in an audit trail, with the entire system built and deployed through an automated CI/CD pipeline.”

The goal is specific (one end-to-end flow), measurable (the acceptance criteria in Section 3), achievable (34 points against a planned 259 hours) and relevant to the main objective of reducing manual classification and routing.

## 7.2 Expected deliverables

Table 15: Sprint 1 deliverables

| No. | Deliverable | Description | Story |
| --- | --- | --- | --- |
| 1 | CI/CD pipeline | Automated build, test and deployment to the staging server with merge protection | US-30 |
| 2 | Authentication module | Citizen registration, OTP verification, login with token and account lock-out | US-06 |
| 3 | Role-based access | Six roles with permissions enforced on APIs and screens | US-08 |
| 4 | Complaint submission module | Complaint form, validation, saving to database with status “Registered” | US-01 |
| 5 | Reference ID and My Complaints | Unique ID generation, confirmation page and list of own complaints | US-03 |
| 6 | Classification service | REST service that returns category, confidence and top keywords; manual-review fallback | US-09 |
| 7 | Routing engine and department queue | Automatic assignment to the department queue with visible routing details | US-13 |
| 8 | Audit trail | Append-only log of login, creation, classification and routing events | US-27 |
| 9 | Documentation, test reports and demo | API documentation, test results, deployment notes and a demonstration of the complete flow on staging to the Product Owner | T39, T40 |

## 7.3 Features completed and items deferred

At the end of the sprint a citizen can register, log in, submit a complaint and see its unique ID; every complaint is classified with a confidence score (low-confidence ones go to manual review) and appears in the correct department queue; users see only what their role permits; every important action is audited; and every change is built, tested and deployed to staging automatically.

Not included in Sprint 1: priority calculation and override (Sprint 2); status updates, field assignment and notifications (Sprints 2 and 3); dashboards, analytics and report export (Sprints 5 and 6).

## 7.4 Sprint schedule and Scrum events

Sprint planning is held on Day 1 (4 hours) and the Daily Scrum every day for 15 minutes. Backlog refinement for Sprint 2 is held on Day 6 (1 hour). On Day 10 the sprint review (1 hour) demonstrates the increment to stakeholders and the retrospective (45 minutes) records what went well and the improvement actions. During the sprint, Days 1–2 are used for set-up, design and data collection, Days 3–7 for building the modules, Days 8–9 for integration and defect fixing, and Day 10 for regression testing, deployment to staging and the review. The ideal burndown is 3.4 story points per day (34 at the start, 17 after Day 5, 0 after Day 10) and is updated daily by the Scrum Master.

## 7.5 Risks and mitigation

Main risks and mitigation: classification accuracy may fall short because of limited data (start with a rule-based baseline, add synthetic data and send low-confidence complaints to manual review); role and permission rules may change late (freeze the permission matrix on Day 2); a team member may be absent (cross-functional tasks, pair working and the 14% buffer); and the sample data may arrive late (use sample data first and replace it later).

# 8. Conclusion

In this workshop I defined the vision and stakeholders of the platform, divided the requirements into nine epics and thirty-three user stories, wrote Given–When–Then acceptance criteria, prioritized the backlog and planned Sprint 1 with eight stories of 34 story points, a 259-hour task breakdown, Planning Poker estimates, a clear sprint goal and a list of deliverables. The team can now deliver a working, tested and auditable increment in two weeks and improve the plan in later sprints using feedback and measured velocity.

Rubrics for Calculation

| Criteria | Excellent (5 Marks) | Good (3 Marks) | Satisfactory (2 Marks) | Needs Improvement (1 Mark) |
| --- | --- | --- | --- | --- |
| Project Vision & Stakeholder Identification (30%) | Project vision is clear, comprehensive, and aligned with the problem statement. All relevant stakeholders and their roles are correctly identified. | Vision is clear with minor omissions. Most stakeholders are correctly identified. | Vision is partially defined. Some stakeholders are missing or incorrectly identified. | Vision is unclear or incomplete. Stakeholders are poorly identified or missing. |
| Epics & User Stories (25%) | Epics are well-defined and user stories are complete, follow Agile format, and fully capture functional requirements. | Epics and user stories are mostly complete with minor formatting or requirement issues. | User stories are partially complete with limited Agile structure. | User stories are incomplete, unclear, or do not follow Agile practices. |
| Acceptance Criteria (20%) | Acceptance criteria are specific, measurable, testable, and aligned with all user stories. | Acceptance criteria are mostly clear and testable with minor gaps. | Acceptance criteria are partially defined and lack clarity or completeness. | Acceptance criteria are missing or not aligned with user stories. |
| Product Backlog Prioritization & Sprint Planning (15%) | Product backlog is logically prioritized, sprint backlog is realistic, and task breakdown is complete. | Backlog prioritization and sprint planning are mostly appropriate with minor issues. | Prioritization or sprint planning is partially complete with limited justification. | Backlog prioritization and sprint planning are poorly organized or incomplete. |
| Story Point Estimation, Sprint Goal & Presentation (10%) | Story point estimation is well justified, sprint goal is clear, deliverables are realistic, and presentation is professional and well organized. | Estimation and sprint goal are mostly appropriate with minor inconsistencies. Presentation is clear. | Estimation or sprint goal lacks justification. Presentation is adequate but incomplete. | Estimation is unrealistic or missing. Sprint goal, deliverables, and presentation are unclear or incomplete. |

| Criteria | Mark |
| --- | --- |
| Project Vision & Stakeholder Identification (30%) | /5 |
| Epics & User Stories (25%) | /5 |
| Acceptance Criteria (20%) | /5 |
| Product Backlog Prioritization & Sprint Planning (15%) | /5 |
| Story Point Estimation, Sprint Goal & Presentation (10%) | /5 |
| TOTAL | /25 |